## Sheet1
SL | Module Name | Menu | Task Details | Task Owner | Time/Day | Status
| Login | Login Page | Login page design | Rokib | 1 Day | Done
|  |  | Login action with authentication | Rokib | 2 Days | Done
| Dashboard | Dashboard | Dashboad with basic data | Rokib | 1 Day | Done
| User Management | User List | Create a user list data grid and display data | Rokib |  | Done
|  |  | Create a user data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual user data details | Rokib |  | Done
|  |  | User data delete operation | Rokib |  | Done
|  |  | Search user data using the search field | Rokib |  | Done
|  | User Create | Create a user data insert form and operation | Rokib |  | Done
| Agents | Agent Create | Create a agent data insert form and operation | Rokib | 5 days | Done
|  | Agent List | Create a agent list data grid and display agents data | Rokib |  | Done
|  |  | Create a agent data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual agent data details | Rokib |  | Done
|  |  | Agent data delete operation | Rokib |  | Done
|  |  | Search agent data using the search field | Rokib |  | Done
| Lead | Create Lead Form | Create a lead form data insert form and operation | Rokib | 5 days | Done
|  | Lead Form List | Create a lead form list data grid and display lead form data | Rokib |  | Done
|  |  | Create a lead form data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual lead form data details | Rokib |  | Done
|  |  | Lead form data delete operation | Rokib |  | Done
|  |  | Search lead form data using the search field | Rokib |  | Done
|  |  | Lead form wise total lead count and lead data show | Rokib |  | Done
|  | Create Dynamic Tables | Create dynamic tables with form, including data type, character, and multiple dynamic fields. | Rokib | 7 days | Done
|  | Dynamic Tables List | Create a dynamic table list data grid and display dynamic table data | Rokib |  | Done
|  |  | Create a dynamic table data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual dynamic table data details | Rokib |  | Done
|  |  | Dynamic table data delete operation | Rokib |  | Done
|  |  | Search dynamic table data using the search field | Rokib |  | Done
|  | Create Lead | Create a lead data insert form with dynamic form and operation | Rokib |  | Done
|  |  | Upload lead via CSV file with dynamic form data insertion. | Rokib |  | Done
|  | Lead List | Create a lead list data grid and display lead data | Rokib | 8 days | Done
|  |  | Create a lead data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual lead data details with a custom dynamic table and add custom lead table data | Rokib |  | Done
|  |  | Lead table data delete operation | Rokib |  | Done
|  |  | Search lead data using the search field | Rokib |  | Done
Done
| Promotion Management | Create Promotion | Create a promotion data insert form and operation | Rokib | 2 days | Done
|  | Promotion List | Create a promotion list data grid and display promotion data | Rokib |  | Done
|  |  | Create a promotion data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual promotion data details | Rokib |  | Done
|  |  | Promotion data delete operation | Rokib |  | Done
|  |  | Search promotion data using the search field | Rokib |  | Done
| Campaign Management | Create Campaign | Create a campaign data insert form and operation | Rokib | 7 days | Done
|  | Campaign List | Create a Campaign list data grid and display Campaign data | Rokib |  | Done
|  |  | Create a Campaign data edit form and implement the edit operation | Rokib |  | Done
|  |  | Show individual Campaign data details | Rokib |  | Done
|  |  | Campaign data delete operation | Rokib |  | Done
|  |  | Search Campaign data using the search field | Rokib |  | Done
|  |  | Upload campaign lead data in CSV format for processing | Rokib |  | Done
|  |  | Show campaign lead email and mobile number data by campaign. | Rokib |  | Done
|  |  | Campaign start/stop option | Rokib |  | Pending
|  | Email | Create email template | Istiak | 5h | Done
|  |  | Email template list and search | Istiak | 2h | Done
|  |  | Email template edit | Istiak | 4h | Done
|  |  | Email template delete | Istiak | 1h | Done
|  |  | Send an email | Istiak | 10h | Done
|  |  | Sended email list and search | Istiak | 2h | Done
|  |  | Send bulk email | Istiak | 16h | Done
|  | SMS | Create SMS template | Istiak | 4h | Done
|  |  | SMS template list and search | Istiak | 2h | Done
|  |  | SMS template edit | Istiak | 4h | Done
|  |  | SMS template delete | Istiak | 1h | Done
|  |  | Send a SMS | Istiak | 8h | Done
|  |  | Sended SMS list and search | Istiak | 2h | Done
|  |  | Send bulk SMS | Istiak | 15h | Done
|  | Tasks | Display tasks in list | Istiak | 8h | Done
|  |  | Task status change | Istiak | 6h | Done
|  |  | Delete task | Istiak | 2h | Done
|  |  | Add and assign task | Istiak | 8h | Done
|  | Products | Produt list and search | Istiak | 4h | Done
|  |  | Add Product | Istiak | 8h | Done
|  |  | Edit Product | Istiak | 8h | Done
|  |  | Product delete | Istiak | 4h | Done
|  | Settings | Country list and search | Istiak | 2h | Done
|  |  | Country add | Istiak | 3h | Done
|  |  | Country edit | Istiak | 2h | Done
|  |  | Country delete | Istiak | 1h | Done
|  |  | Currency list and search | Istiak | 2h | Done
|  |  | Currency add | Istiak | 3h | Done
|  |  | Currency edit | Istiak | 2 h | Done
|  |  | Currency delete | Istiak | 1 h | Done
|  | Task Planning | Planing about task and distribute to the members | Hasan | 3d | Done
|  | Basic Architecture | Thinking about coding structure and take time db design and help members to db design and coding instruction | Hasan | 5d | Done
|  | Authentication | User login and registration process done in both api and view level | Hasan | 2d | Done
|  | Authorization | Authorized valid user via middlewire | Hasan | 2d | Done
|  | User Module | user list, user crud, user serach with data validation | Hasan | 7d | Done
|  | Role Management | done user role management | Hasan | 5d | Done
|  | Permission Management | Full permisison crud with data validation | Hasan | 5d | Done
|  | Menu settings | Menu settings with dynamic route channel | Hasan | 3d | Done
|  | Dynamic Template | Template dynamic from static html | Hasan | 1d | Done
|  | Bug Fixing | Fix busg on each module and help team members to fix the problems | Hasan | 5d | Done
|  | Lead Form Planing | Working with lead form and planning with team member and implementing finally | Hasan | 1d | Done
|  | Form Management Planning | Design full form management and working on it | Hasan | 2d | Done
|  | Testing | Had to test all of the features | Hasan | 7d | Done
|  | Design on Templates | Changed some design in template for better look | Hasan | 5d | Done